## Worksheet
Strategy Planning - Project Template
Office Use ¦ Template Type: Project Template ¦ Purpose: Strategy Planning
Phase | Objective | Key Activities | Responsible Team/Person | Timeline (Start - End) | Status
Initiation | Define strategic goals and scope of the project. | - Conduct stakeholder interviews - Identify key objectives - Develop initial project charter | Project Sponsor & PMO | Jan 5 - Jan 12, 2024 | In Progress
Analysis | Evaluate market trends and internal capabilities. | - SWOT analysis - Competitive benchmarking - Risk assessment | Strategy Team & Analytics | Jan 15 - Jan 26, 2024 | Not Started
Planning | Create detailed action plans and resource allocation. | - Develop work breakdown structure - Assign roles and responsibilities - Budget planning & approval | Project Manager & Finance | Jan 29 - Feb 9, 2024 | Not Started
Execution | Implement strategy initiatives across departments. | - Roll out pilot programs - Monitor KPIs and milestones - Conduct weekly progress meetings | All Department Heads | Feb 12 - Apr 30, 2024 | Not Started
Monitoring & Control | Track performance and adjust strategy as needed. | - Monthly review meetings - Dashboard reporting - Change request management | PMO & Steering Committee | Mar 1 - Apr 30, 2024 | Not Started
Closure | Finalize project deliverables and document outcomes. | - Final performance review - Lessons learned session - Formal project closure report | Project Manager & Sponsor | May 1 - May 10, 2024 | Not Started
Total Duration: |  |  |  |  | May 10, 2024