## Worksheet
STRATEGY PLANNING PROJECT TEMPLATE
Personal Use - Template Type: Project Template ¦ Purpose: Strategy Planning
Phase | Objective | Key Actions | Responsible Party | Status | Dates (Start - End)
1. Initiation | Define project vision and scope | - Identify strategic goals - Gather stakeholder input - Document project charter | Project Owner | In Progress | 2024-04-01 - 2024-04-15
2. Analysis | Evaluate internal and external factors | - Conduct SWOT analysis - Assess market trends - Review resource availability | Strategy Team | Planned | 2024-04-16 - 2024-05-05
3. Planning | Create detailed execution roadmap | - Develop timeline and milestones - Allocate budget and resources - Identify risks and mitigation plans | Project Manager | To Do | 2024-05-06 - 2024-05-31
4. Execution | Implement strategy with defined actions | - Begin project tasks - Monitor progress weekly - Hold status review meetings | Team Members | To Do | 2024-06-01 - 2024-08-31
5. Monitoring & Evaluation | Track performance and adapt as needed | - Measure KPIs - Conduct mid-project review - Update plans based on feedback | Project Owner & PM | To Do | 2024-09-01 - 2024-10-31
6. Closure | Finalize project and document outcomes | - Deliver final results - Compile lessons learned - Share success report with stakeholders | Project Owner | To Do | 2024-11-01 - 2024-11-30
Total Project Duration: |  |  | 2024-04-01 to 2024-11-30