## Worksheet
STRATEGY PLANNING - PROJECT TEMPLATE
Phase | Objective | Key Activities | Responsible Team/Person | Timeline (Start - End) | Status
Initiation | Define project vision and scope | - Conduct stakeholder interviews - Establish success criteria - Draft project charter | Project Sponsor, PMO | Jan 01 - Jan 15, 2024 | In Progress
Research & Analysis | Gather and analyze strategic data | - Market research - Competitor analysis - SWOT assessment | Market Research Team, Strategy Analysts | Jan 16 - Feb 10, 2024 | Pending
Strategy Development | Create actionable strategic plans | - Develop strategic objectives - Design implementation roadmap - Risk assessment planning | Strategy Team, Department Leads | Feb 11 - Mar 05, 2024 | Pending
Approval & Planning | Secure executive approval and finalize budget | - Prepare presentation for leadership - Finalize budget allocation - Obtain sign-off on project plan | Project Manager, Finance Team | Mar 06 - Mar 20, 2024 | Pending
Execution Launch | Begin implementation phase | - Kickoff meeting - Assign team roles - Begin first milestone tasks | Project Manager, Implementation Team | Mar 21 - Apr 05, 2024 | Pending
Critical Success Factors
Stakeholder Alignment |  | Regular communication and feedback loops with all key stakeholders | Project Manager | Continuous | In Progress
Resource Availability |  | Ensure team members and budget are secured prior to phase start | HR & Finance Departments | Pre-phase 1 | In Progress
Progress Tracking |  | Daily standups, weekly status reports, and monthly reviews | Project Manager, Team Leads | Ongoing | In Progress