## Worksheet
Phase | Objective | Key Activities | Responsible Team Member | Start Date | End Date | Status
1. Research & Analysis | Evaluate market trends and business environment | Conduct SWOT analysis, competitor review, customer surveys | Marketing Manager | 2023-10-01 | 2023-10-15 | Pending
2. Goal Setting | Define SMART business objectives for the next fiscal year | Workshop with leadership team, prioritize goals, align KPIs | CEO & Executive Team | 2023-10-16 | 2023-10-25 | In Progress
3. Strategy Development | Create actionable strategic initiatives | Develop growth, marketing, operations plans; risk assessment | Strategy Team Lead | 2023-10-26 | 2023-11-10 | In Progress
4. Resource Allocation | Assign budget, personnel, and tools to each initiative | Budget planning, team assignments, timeline alignment | Finance & HR Managers | 2023-11-11 | 2023-11-20 | Pending
5. Implementation Plan | Develop detailed execution roadmap with milestones | Create project schedules, assign owners, set review points | Project Manager | 2023-11-21 | 2023-11-30 | Pending
6. Review & Approval | Finalize strategy with leadership sign-off | Presentation to board, feedback collection, final adjustments | CEO & Board Members | 2023-12-01 | 2023-12-05 | Pending
Total Duration: 6 Weeks (Approx. 42 Days)