## Worksheet
Startup Strategy Planning Project Template
Phase | Key Objective | Deliverables | Timeline (Weeks) | Responsible Team/Person | Status
Phase 1: Vision & Mission | Define core purpose, vision, and mission statement for the startup. | Finalized vision/misson document, stakeholder alignment | 1-2 | CXO Team & Founders | In Progress
Phase 2: Market Research | Identify target market, customer segments, and competitive landscape. | Market analysis report, customer personas | 3-5 | Product & Marketing Teams | Pending
Phase 3: Value Proposition | Develop clear and compelling value proposition for target users. | Value proposition canvas, pitch deck section | 6-7 | Product & Strategy Team | Pending
Phase 4: Go-to-Market Strategy | Create launch plan, sales channels, and initial marketing tactics. | GTM strategy document, launch calendar | 8-10 | Marketing & Sales Team | Pending
Phase 5: MVP Planning | Define minimum viable product scope and feature set. | MVP roadmap, feature prioritization matrix | 11-12 | Product & Engineering Teams | Pending
Phase 6: Funding & Investor Readiness | Prepare financial projections, pitch deck, and investor materials. | Funding proposal package, financial model | 13-15 | Finance & Founders | Pending
Phase 7: Execution & Launch | Execute GTM strategy and launch MVP to early adopters. | Live product release, user feedback collection | 16-20 | All Teams (Cross-functional) | Pending
Phase 8: Review & Iterate | Analyze performance data and refine strategy based on feedback. | Post-launch review report, iteration plan | 21+ | Strategy & Product Teams | Pending