## Worksheet
Project Timeline - Strategy Planning (Advanced)
Phase | Task | Start Date | End Date | Responsible Team | Status | Budget (USD)
Phase 1: Discovery & Assessment
Conduct market analysis, stakeholder interviews, and SWOT assessment.
Phase 1 | Market Research | 2025-04-01 | 2025-04-15 | Research Team | In Progress | $8,500
Phase 1 | Stakeholder Interviews (15) | 2025-04-16 | 2025-04-30 | Planning Office | In Progress | $6,750
Phase 2: Strategy Development
Define strategic objectives, KPIs, and high-level roadmap.
Phase 2 | Define Strategic Objectives | 2025-05-01 | 2025-05-10 | C-Suite & Strategy Board | Delayed | $4,800
Phase 2 | Develop KPI Framework | 2025-05-11 | 2025-05-18 | Data Analytics Team | Completed | $3,900
Phase 3: Roadmap & Execution Planning
Create detailed project plans, assign resources, and set milestones.
Phase 3 | Build Execution Roadmap | 2025-05-19 | 2025-06-10 | Project Management Office (PMO) | In Progress | $18,400
Phase 3 | Resource Allocation & Budget Finalization | 2025-06-11 | 2025-06-18 | Finance & HR Teams | Delayed | $7,350
Phase 4: Approval & Go-Live Readiness
Submit strategy for executive approval and prepare implementation tools.
Phase 4 | Executive Review & Approval | 2025-06-19 | 2025-07-05 | C-Suite & Board Members | In Progress | $3,800
Total Project Budget: | [5 empty] | $54,500