## Worksheet
STRATEGY PLANNING - PROJECT TIMELINE (ANALYSIS VIEW)
Phase / Task | Start Date | End Date | Duration (Days) | Status | Responsible Team/Person | Description / Key Metrics
PHASE 1: RESEARCH & ANALYSIS
Market Research & Competitor Analysis | 2024-01-05 | 2024-01-31 | 27 | In Progress | Maria Chen (Research) | Gather data on market trends, customer behavior, and competitive positioning.
Initial Findings Review Meeting | 2024-01-31 | 2024-01-31 | 1 | Closed (Completed) | Maria Chen, James Kim (Leadership) | Present key insights and validate strategic assumptions.
PHASE 2: STRATEGIC DEVELOPMENT
Define Core Strategy Objectives | 2024-02-01 | 2024-02-15 | 15 | Critical Path | Sarah Johnson (Strategy) | Establish 3–5 high-level goals aligned with company vision.
Develop Strategic Initiatives Framework | 2024-02-16 | 2024-03-10 | 23 | Critical Path | Sarah Johnson, David Lee (Ops) | Map initiatives to objectives with KPIs and ownership.
PHASE 3: VALIDATION & APPROVAL
Internal Strategy Workshop | 2024-03-11 | 2024-03-15 | 5 | Closed (Completed) | All Cross-functional Leads, Sarah Johnson (Strategy) | Review and align on strategic direction with stakeholder input.
PHASE 4: PLANNING & EXECUTION READINESS
Finalize Project Timeline & Budget | 2024-03-16 | 2024-03-31 | 16 | Critical Path | Sarah Johnson, Emily Wong (Finance) | Integrate all initiatives into consolidated timeline and budget.
PHASE 5: STRATEGY LAUNCH
Strategy Rollout Kickoff | 2024-04-01 | 2024-04-01 | 1 | Pending (Upcoming) | All Departments, Leadership Team | Official launch of strategic plan with communication campaign.
PROJECT SUMMARY
Total Duration | 2024-01-05 to 2024-04-01 |  | 87 Days | All critical milestones on track.