## Worksheet
Project Timeline - Strategy Planning
Phase | Activity/Task | Start Date | End Date | Responsible Party | Status
Initiation | Define Project Scope & Objectives | 2024-01-05 | 2024-01-15 | Project Manager | In Progress
Planning | Develop Strategy Framework | 2024-01-16 | 2024-01-31 | Strategy Team | Pending
Planning | Create Resource Allocation Plan | 2024-02-01 | 2024-02-15 | Finance & HR Departments | Pending
Execution | Launch Pilot Implementation Phase 1 | 2024-02-16 | 2024-03-15 | Implementation Team | Pending
Execution | Conduct Stakeholder Feedback Session | 2024-03-16 | 2024-03-31 | Project Manager & Stakeholders | Pending
Monitoring & Evaluation | Analyze Pilot Results & Adjust Strategy | 2024-04-01 | 2024-04-15 | Strategy Team & Analytics Group | Pending
Closure | Finalize Full-Scale Rollout Plan | 2024-04-16 | 2024-05-15 | Executive Leadership | Pending
Key Milestones
Project Kickoff |  | 2024-01-05 | Initiation Phase Complete
Strategy Approval |  | 2024-01-31 | Planning Phase Complete
Pilot Launch Complete |  | 2024-03-15 | Execution Phase Midpoint
Final Strategy Review |  | 2024-04-15 | Evaluation Complete
Full Rollout Approved |  | 2024-05-15 | Project Closure Achieved