## Project Timeline - Client View
Project Timeline - Client View
Strategy Planning ¦ Q3 2024 – Q2 2025
Phase | Objective | Start Date | End Date | Status | Responsible Team
Initiation & Discovery | Evaluate business goals, market needs, and client requirements. | 2024-07-01 | 2024-07-31 | Completed | Strategy Team
Market & Competitor Analysis | Analyze industry trends and competitive positioning. | 2024-08-01 | 2024-08-31 | Completed | Market Research Unit
Goal & KPI Definition | Define measurable objectives and performance indicators. | 2024-09-01 | 2024-09-15 | In Progress | Strategy & Analytics Team
Core Strategy Development | Create actionable strategic framework and roadmap. | 2024-09-16 | 2024-10-31 | In Progress | Strategy Team & Leadership
Stakeholder Alignment Workshop | Collaborate with key stakeholders on strategic direction. | 2024-11-01 | 2024-11-08 | Completed | Client Engagement Team
Phase Review & Approval | Present final strategy for client sign-off. | 2024-11-09 | 2024-11-30 | In Progress | Executive & Client Review Panel
Implementation Planning Phase | Translate strategy into execution milestones. | 2024-12-01 | 2025-01-31 | Delayed | Execution & Project Management Team
Q1 2025 Kickoff & Reporting | Begin execution and launch performance monitoring. | 2025-01-01 | 2025-03-31 | Completed | All Teams
Mid-Year Review (Q2) | Evaluate performance and adjust strategy as needed. | 2025-04-01 | 2025-06-30 | Completed | Strategy & Analytics Team