## Worksheet
Phase | Task | Start Date | End Date | Owner | Status
Initiation | Define Project Scope | 2024-01-05 | 2024-01-15 | John Doe | In Progress
Planning | Develop Work Breakdown Structure | 2024-01-16 | 2024-01-30 | Jane Smith | Not Started
Execution | Resource Allocation | 2024-02-01 | 2024-02-15 | Mike Johnson | Not Started
Execution | Begin Development | 2024-02-16 | 2024-03-30 | Sarah Lee | Not Started
Monitoring | Weekly Progress Review | 2024-03-01 | 2024-03-31 | John Doe | Not Started
Closure | Final Project Review & Handover | 2024-04-01 | 2024-04-15 | Jane Smith | Not Started