## Worksheet
Project Timeline - Strategy Planning
Dashboard View ¦ Q3 2024
Phase | Task Name | Start Date | End Date | Status | Owner | Action
Discovery & Planning
Phase 1 | Market Research & Analysis | 2024-07-01 | 2024-07-15 | On Track | Jane Doe | Review
Phase 1 | Stakeholder Alignment Workshop | 2024-07-16 | 2024-07-18 | On Track | Mark Lee | Review
Design & Development
Phase 2 | User Persona Creation | 2024-07-19 | 2024-07-31 | Delayed (3 days) | Sarah Kim | Update
Phase 2 | Wireframe Prototyping | 2024-08-01 | 2024-08-15 | On Track | Liam Chen | Review
Testing & Validation
Phase 3 | Usability Testing Session 1 | 2024-08-16 | 2024-08-31 | On Track | Ava Thompson | Schedule
Phase 3 | Feedback Integration & Rework | 2024-09-01 | 2024-09-15 | Not Started | Daniel Brown | Start Now
Launch & Review
Phase 4 | Final QA & Compliance Check | 2024-09-16 | 2024-09-30 | Not Started | Emma White | Start Now
Phase 4 | Go-Live & Post-Launch Review | 2024-10-01 | 2024-10-15 | Not Started | James Wilson | Start Now
Project Progress: |  |  | 75% Complete