## Worksheet
Phase | Task | Start Date | End Date | Duration (Days) | Status | Responsible Team(Owner) | Milestones
Initiation | Define Project Scope & Objectives | 2024-01-01 | 2024-01-15 | 15 | In Progress | Project Manager(Jane Doe) | Approved Scope Document (Jan 14, 2024)
Planning | Develop Detailed Work Breakdown Structure (WBS) | 2024-01-16 | 2024-01-31 | 16 | Pending | Project Planner (John Smith) | WBS Finalized (Jan 30, 2024)
Planning | Create Gantt Chart & Timeline Schedule | 2024-01-31 | 2024-02-15 | 15 | Pending | Scheduling Lead (Sarah Lee) | Schedule Approved (Feb 14, 2024)
Execution | Resource Allocation & Team Onboarding | 2024-02-16 | 2024-03-01 | 14 | Pending | HR & Ops (Mike Johnson) | Team Onboarded (Mar 01, 2024)
Execution | Phase 1 Development (Core Features) | 2024-03-02 | 2024-05-15 | 75 | Pending | Development Team (Alex Brown) | Alpha Release (Apr 30, 2024)
Execution | Phase 1 Testing & QA | 2024-05-16 | 2024-06-30 | 45 | Pending | QA Team (Linda Chen) | Bug Resolution Complete (Jun 28, 2024)
Closure | User Acceptance Testing (UAT) | 2024-07-01 | 2024-07-31 | 31 | Pending | Product Owner (David Kim) | UAT Sign-off (Jul 30, 2024)
Closure | Final Deployment & Go-Live | 2024-08-01 | 2024-08-15 | 15 | Pending | IT Operations (Rachel Green) | Go-Live Confirmed (Aug 14, 2024)
Closure | Post-Implementation Review & Documentation | 2024-08-16 | 2024-09-30 | 45 | Pending | Project Manager (Jane Doe) | Final Report Submitted (Sep 29, 2024)
Total Project Duration: | [5 empty] | 305 days