## Worksheet
Strategy Planning - Project Timeline (Employee View)
Employee Name | Role | Task Description | Start Date | End Date | Status
Alice Johnson | Project Manager | Initiate Strategic Planning Workshop | 2024-04-01 | 2024-04-05 | In Progress
Bob Smith | Business Analyst | Conduct Market Research & Competitor Analysis | 2024-04-03 | 2024-04-15 | In Progress
Carol Davis | Marketing Specialist | Develop Brand Positioning Strategy | 2024-04-10 | 2024-04-25 | Pending
David Miller | Product Lead | Create Product Roadmap for Q3 Launch | 2024-04-12 | 2024-05-10 | In Progress
Eva Brown | Financial Analyst | Prepare Budget Forecast & Financial Modeling | 2024-04-15 | 2024-04-30 | Completed
Frank Wilson | Operations Coordinator | Organize Cross-Functional Alignment Meeting | 2024-04-18 | 2024-04-21 | Completed
Grace Lee | UX Designer | Design User Experience for New Platform Features | 2024-04-20 | 2024-05-15 | Pending