## Worksheet
Phase | Task Name | Start Date | End Date | Status | Responsible Team | Budget (USD)
Phase 1: Discovery | Market & Competitor Research | 2024-04-01 | 2024-04-15 | In Progress | Strategy Team | $15,000
| Stakeholder Interviews & Needs Assessment | 2024-04-16 | 2024-05-15 | In Progress | Product & Marketing Team | $8,000
| SWOT Analysis Completion | 2024-05-16 | 2024-05-31 | Pending | Strategy Team | $5,000
Phase 2: Planning | Define Strategic Objectives | 2024-06-01 | 2024-06-15 | Pending | Executives & Strategy Team | $3,500
| Create Roadmap & Milestones | 2024-06-16 | 2024-07-15 | Pending | Project Management Office | $7,800
| Risk Assessment & Mitigation Planning | 2024-07-16 | 2024-08-31 | Pending | Risk Management Team | $6,500
| Finalize Strategy Proposal for Approval | 2024-09-01 | 2024-11-30 | Pending | Executive Committee | $4,500
Phase 3: Implementation | Resource Allocation & Team Onboarding | 2025-01-01 | 2025-01-31 | Pending | HR & Operations Team | $48,900
| Development of Key Deliverables (Phase 1) | 2025-02-01 | 2025-04-30 | Pending | R&D Team | $97,600
| Internal Testing & Validation Cycle 1 | 2025-05-01 | 2025-06-30 | Pending | QA Team | $34,750
| Marketing Launch Campaign Setup (Phase 1) | 2025-07-01 | 2025-08-31 | Pending | Marketing Team | $65,400
| User Training & Onboarding Program Development | 2025-09-01 | 2025-11-30 | Pending | Training & Support Team | $46,850
| Go-Live & System Deployment (Core Release) | 2025-12-01 | 2025-12-31 | Pending | IT & Project Team | $89,300
Phase 4: Evaluation | Post-Launch Performance Review (Q1) | 2026-01-01 | 2026-03-31 | Pending | Data Analytics Team | $45,500
| User Feedback Collection & Analysis | 2026-04-01 | 2026-06-30 | Pending | Customer Success Team | $38,750
| Final Strategy Report & Continuous Improvement Recommendations | 2026-07-01 | 2026-09-30 | Pending | Strategy Team & Executives | $35,450
Total Estimated Budget: | [5 empty] | $629,450
Note: This timeline is subject to adjustment based on stakeholder feedback, market changes, and resource availability. Milestones marked as "Critical" require executive-level oversight.