## Worksheet
Project Timeline - Freelancer Style
Task/Phase | Start Date | End Date | Duration (Days) | Status
Project Initiation & Planning | 2023-10-01 | 2023-10-05 | 5 | Completed
Requirements Gathering | 2023-10-06 | 2023-10-12 | 7 | Completed
Design Phase - UI/UX Mockups | 2023-10-13 | 2023-10-24 | 12 | In Progress
Development - Frontend | 2023-10-25 | 2023-11-15 | 21 | In Progress
Development - Backend Integration | 2023-10-25 | 2023-11-29 | 35 | In Progress
Testing & Quality Assurance | 2023-11-30 | 2023-12-15 | 16 | Delayed
User Training & Documentation | 2023-12-16 | 2023-12-20 | 5 | Delayed
Launch & Deployment | 2023-12-21 | 2023-12-31 | 11 | Delayed