## Worksheet
Project Timeline - Strategy Planning
Phase | Task | Start Date | End Date | Status | Responsible Team Member
Planning | Define Objectives & Scope | 2024-01-05 | 2024-01-15 | In Progress | Jane Doe
Research & Analysis | Market & Competitor Research | 2024-01-16 | 2024-01-31 | Pending | John Smith
Strategy Development | Create Strategic Framework | 2024-02-01 | 2024-02-15 | Pending | Alice Brown
Implementation Planning | Develop Action Plan & Timeline | 2024-02-16 | 2024-03-01 | Pending | Robert Wilson
Review & Approval | Leadership Review & Final Sign-off | 2024-03-02 | 2024-03-10 | Pending | Susan Lee
Template Version: Home Use ¦ Created for Strategy Planning ¦ Date Generated: 2024-01-04