## Worksheet
Project Timeline - Strategy Planning
Large Business Edition ¦ Q3 2024 – Q2 2025
Phase / Milestone | Start Date | End Date | Status | Owner(s) | Progress
Phase 1: Strategic Assessment & Market Analysis
Executive Stakeholder Workshop | 2024-07-15 | 2024-07-18 | Completed | CFO, COO, CTO
Market Positioning Research | 2024-07-19 | 2024-08-31 | Completed | Market Insights Team
Competitor Benchmarking Report | 2024-08-15 | 2024-09-30 | Completed | Strategy & Analytics Group
Phase 2: Goal Definition & Objective Setting
Long-Term Vision Document Draft | 2024-10-01 | 2024-10-31 | Completed | CXO Leadership Team
Key Performance Indicators (KPIs) Finalization | 2024-11-05 | 2024-11-30 | Completed | Finance & Performance Office
Phase 3: Action Planning & Resource Allocation
Departmental Strategy Alignment Workshop | 2024-12-01 | 2024-12-15 | Completed | All Department Heads
Resource Budgeting & Forecasting | 2024-12-16 | 2025-01-31 | Completed | Finance, HR, Operations
Phase 4: Execution & Monitoring
Implementation Kickoff - Q1 2025 | 2025-01-01 | 2025-03-31 | Ongoing | Project Management Office (PMO)
Monthly Review & Adjustment | 2025-01-15 | 2025-04-30 | Ongoing | CXO Team & PMO
Phase 5: Evaluation & Continuous Improvement
Q2 Performance Review & Reporting | 2025-04-15 | 2025-06-30 | Delayed (Pending) | Performance Analytics Team
Total Duration | 2024-07-15 | 2025-06-30 | Approx. 11.5 months ¦ Project Success Rate: 89%
Note:This timeline is subject to review and adjustment based on quarterly business reviews and strategic shifts.
Prepared by: Strategy Planning Office ¦ Updated: June 1, 2024