## Worksheet
Strategy Planning - Project Timeline (Manager View)
Phase / Milestone | Start Date | End Date | Owner | Status | Budget Allocated ($)
Phase 1: Initiation & Strategy Definition
Stakeholder Alignment Workshop | 2024-03-01 | 2024-03-05 | Jane Smith (Project Lead) | On Track | 15,000
Business Objective Finalization | 2024-03-06 | 2024-03-15 | Jane Smith (Project Lead) | On Track | 12,500
Phase 2: Planning & Resource Allocation
Project Scope Document Finalization | 2024-03-16 | 2024-03-25 | Mike Johnson (PMO) | On Track | 8,500
Project Kickoff Meeting | 2024-03-26 | 2024-03-26 | Jane Smith (Project Lead) | Completed | 5,000
Phase 3: Execution & Monitoring
Development Sprint 1 (Core Features) | 2024-03-27 | 2024-04-15 | Alice Brown (Tech Lead) | On Track | 65,000
Sprint 1 Review & Feedback Session | 2024-04-16 | 2024-04-18 | Alice Brown (Tech Lead) | Completed | 3,500
Phase 4: Testing & Validation
QA Testing Cycle 1 (Regression) | 2024-04-19 | 2024-05-03 | Lisa Wong (QA Manager) | On Track | 38,000
User Acceptance Testing (UAT) Start | 2024-05-15 | 2024-05-31 | Mark Taylor (Product Owner) | Delayed | 35,000
Phase 5: Deployment & Closure
Production Deployment (Phase 1) | 2024-06-01 | 2024-06-15 | Tom Wilson (DevOps) | On Track | 48,500
Project Final Review & Sign-Off | 2024-06-16 | 2024-06-30 | Jane Smith (Project Lead) | On Track | 15,000
Total Project Cost | Estimated Total: |  |  |  | $300,500