## Worksheet
Phase | Task | Start Date | End Date | Status | Responsible Team/Person
Phase 1: Strategy Development | Define strategic objectives and vision | 2023-09-01 | 2023-09-15 | In Progress | Executive Leadership Team
| Conduct market and competitor analysis | 2023-09-16 | 2023-09-30 | In Progress | Market Research Department
| Develop strategic roadmap outline | 2023-10-01 | 2023-10-15 | Pending | Strategy Planning Team
| Present and finalize strategy to stakeholders | 2023-10-16 | 2023-10-25 | Pending | CEO & Board of Directors
Phase 2: Project Planning | Break down roadmap into deliverables and milestones | 2023-10-26 | 2023-11-15 | Pending | Project Management Office (PMO)
| Assign resources and team responsibilities | 2023-11-16 | 2023-11-30 | Pending | Hiring & HR Department
| Finalize project timeline and budget approval | 2023-12-01 | 2023-12-15 | Pending | CFO & Project Steering Committee
Phase 3: Execution | Launch initial project phases and pilot programs | 2023-12-16 | 2024-01-31 | Pending | Project Delivery Teams
| Monthly performance reviews and KPI tracking | 2024-02-01 | Ongoing | Pending | Performance Management Team
Milestone: Project Launch Complete (Q1 2024)
| Phase 4: Monitoring & Review | Quarterly strategy review meetings | 2024-04-01 | Ongoing | Pending | Strategy Team & Executives
Evaluate ROI and impact metrics post-launch |  | 2024-06-30 | 2024-07-31 | Pending | Analytics & Finance Teams
Update strategy for next fiscal year based on insights |  | 2024-08-01 | 2024-08-31 | Pending | Executive Leadership Team
Total Duration: September 1, 2023 – August 31, 2024