## Worksheet
Project Timeline - Strategy Planning
One Page Template ¦ Comprehensive Overview of Key Milestones and Activities
Phase / Milestone | Start Date | End Date | Status | Responsible Team | Description
Initiation & Scoping | 2024-01-05 | 2024-01-19 | In Progress | Project Leadership | Define project vision, objectives, and scope with stakeholder alignment.
Market & Competitive Analysis | 2024-01-20 | 2024-01-31 | Pending | Business Intelligence Team | Conduct research on market trends, customer needs, and competitor strategies.
Strategy Development Workshop | 2024-02-01 | 2024-02-15 | Pending | Strategic Planning Team | Facilitate collaborative session to define key strategies and KPIs.
Resource Allocation & Budgeting | 2024-02-16 | 2024-03-01 | Pending | Finance & HR Departments | Determine team composition, budget approval, and resource planning.
Execution Phase I: Launch Preparation | 2024-03-02 | 2024-03-15 | Pending | All Departments | Finalize launch materials, internal training, and system readiness.
Go-Live & Initial Rollout | 2024-03-16 | 2024-03-31 | Pending | Operations & Marketing Teams | Official launch of new strategy with targeted pilot groups.
Monitoring & Feedback Collection | 2024-04-01 | 2024-05-15 | Pending | Data Analytics Team | Collect KPIs, user feedback, and performance metrics.
Review & Optimization Phase | 2024-05-16 | 2024-06-30 | Pending | Executive Board & Strategy Team | Evaluate results, identify improvements, and refine approach.
Final Reporting & Documentation | 2024-07-01 | 2024-07-15 | Pending | Project Management Office (PMO) | Compile final report, lessons learned, and official closure.