## Worksheet
Project Timeline - Planning View
Phase | Task Name | Start Date | End Date | Responsible | Status
Initiation | Define Project Scope | 2024-01-05 | 2024-01-15 | Jane Doe | Pending
Initiation | Secure Stakeholder Approval | 2024-01-16 | 2024-01-25 | John Smith | In Progress
Planning | Create Detailed Project Plan | 2024-01-26 | 2024-02-10 | Mary Johnson | Pending
Planning | Resource Allocation & Scheduling | 2024-02-11 | 2024-02-18 | Alex Brown | In Progress
Execution | Begin Development Phase 1 | 2024-02-19 | 2024-03-15 | Lisa White | Pending
Execution | Testing & QA Verification | 2024-03-16 | 2024-04-10 | Tom Green | Pending
Closing | Final Review & Sign-off | 2024-04-11 | 2024-04-20 | Jane Doe | Pending
Closing | Project Documentation & Handover | 2024-04-21 | 2024-04-30 | Mary Johnson | Pending
Total Duration: |  |  |  |  | 2024-01-05 to 2024-04-30