## Worksheet
Project Timeline - Strategy Planning
Printable Template ¦ Version 1.0 ¦ Prepared on:
Phase / Milestone | Start Date | End Date | Status | Responsible Team
Initiation & Planning | 2024-01-05 | 2024-01-15 | Completed | Strategy Team
Market Research & Analysis | 2024-01-16 | 2024-01-31 | Completed | Research Department
Objective Setting & KPIs Definition | 2024-02-01 | 2024-02-15 | In Progress | Executive Leadership
Action Plan Development | 2024-02-16 | 2024-03-15 | In Progress | Operations Team
Resource Allocation & Budgeting | 2024-03-16 | 2024-03-31 | Delayed | Finance Department
Stakeholder Alignment Workshop | 2024-04-01 | 2024-04-15 | Delayed | Project Management Office
Final Review & Approval | 2024-04-16 | 2024-05-15 | Delayed | Executive Board
Strategy Rollout (Phase 1) | 2024-05-16 | 2024-07-31 | Delayed | All Departments