## Worksheet
Project Timeline - Strategy Planning
Phase / Milestone | Start Date | End Date | Status | Responsible Team
Initiation & Planning | 2024-01-15 | 2024-01-31 | Upcoming | Project Management Office (PMO)
Market Analysis & Research | 2024-02-01 | 2024-03-15 | Upcoming | Business Intelligence Team
Strategy Development Workshop | 2024-03-16 | 2024-03-25 | Upcoming | Executive Leadership & Strategy Team
Stakeholder Alignment Meeting | 2024-03-26 | 2024-04-10 | Upcoming | Product & Sales Teams
Resource Allocation Finalization | 2024-04-11 | 2024-05-31 | Upcoming | HR & Finance Departments
Implementation Phase 1 Launch | 2024-06-01 | 2024-07-31 | Upcoming | Development & Operations Team
Performance Review & Adjustment | 2024-08-01 | 2024-09-30 | Upcoming | Strategy & Analytics Team
Full Rollout & Evaluation | 2024-10-01 | 2024-11-30 | Upcoming | All Departments