## Worksheet
Strategy Planning - Project Timeline Report
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Phase 1: Strategy Definition & Alignment
1.1 | Conduct Strategic Environment Analysis | 2024-03-01 | 2024-03-15 | Completed | Leadership Team
1.2 | Define Core Objectives & KPIs | 2024-03-16 | 2024-03-31 | Completed | Strategy Unit
Phase 2: Plan Development & Approval
2.1 | Develop Tactical Implementation Plans | 2024-04-01 | 2024-04-15 | In Progress | Project Managers
2.2 | Internal Review & Feedback Collection | 2024-04-16 | 2024-04-30 | In Progress | Stakeholder Committee
2.3 | Finalize & Present Strategy to Executives | 2024-05-01 | 2024-05-15 | In Progress | C-Suite Office
Phase 3: Execution & Monitoring
3.1 | Launch Pilot Initiatives (Q2) | 2024-05-16 | 2024-06-30 | Delayed | Operations Team
3.2 | Monthly Review & Adjustment Meetings | 2024-07-01 | Ongoing | In Progress | Project Steering Committee
Phase 4: Evaluation & Optimization
4.1 | Q3 Performance Review & Reporting | 2024-09-01 | 2024-09-30 | Delayed | Analytics Team
4.2 | Final Strategy Optimization & Presentation | 2024-10-01 | 2024-10-31 | In Progress | Strategy Unit
Total Duration: |  |  |  | 2024-03-01 to 2024-10-31
Current Status: |  |  |  | On Track (60% Complete)