## Worksheet
Phase | Task | Start Date | End Date | Owner | Status
Discovery & Research | Market Analysis & Competitive Review | 2024-01-15 | 2024-01-31 | Alice Chen | In Progress
Product Design | User Persona Development | 2024-02-01 | 2024-02-15 | James Reed | Pending
| Wireframing & Prototyping | 2024-02-16 | 2024-03-15 | Sarah Kim | Pending
Development Phase | Frontend Development (MVP) | 2024-03-18 | 2024-05-15 | Tomás Silva | Pending
| Backend Infrastructure Setup | 2024-03-18 | 2024-05-15 | Laura Bennett | Pending
| API Integration & Testing | 2024-05-16 | 2024-06-30 | Raj Patel | Pending
Launch Preparation | Alpha Testing & Feedback Collection | 2024-07-01 | 2024-07-31 | Alice Chen | Pending
| Marketing & PR Campaign Setup | 2024-07-15 | 2024-08-15 | Maria Lopez | Pending
Go-Live & Review | Official Product Launch | 2024-08-16 | 2024-08-16 | All Team Members | Pending
Post-Launch Review | Performance Evaluation & Iteration Planning | 2024-08-17 | 2024-09-15 | Alice Chen, James Reed | Pending