## Worksheet
Phase | Key Milestones | Start Date | End Date | Responsible Team | Status
Initiation | Project Kickoff, Stakeholder Alignment | 2024-01-15 | 2024-01-31 | Project Management Office | In Progress
Planning | Resource Allocation, Risk Assessment, Budget Finalization | 2024-02-01 | 2024-03-15 | Strategy & Finance Teams | Pending Review
Execution | Task Deployment, Team Coordination, Quality Checks | 2024-03-16 | 2024-07-31 | All Project Teams | Not Started
Monitoring & Evaluation | Status Reporting, KPI Tracking, Adjustments Implementation | 2024-08-01 | 2024-11-30 | Project Control Center | Not Started
Closure | Final Deliverables, Stakeholder Sign-off, Lessons Learned Session | 2024-12-01 | 2024-12-31 | Project Management Office & Steering Committee | Not Started
Summary View – Strategy Planning Project Timeline ¦ Total Duration: 12 Months (Jan 2024 - Dec 2024)