## Worksheet
Strategy Planning - Project Timeline Template
Phase/Stage | Key Objectives | Start Date | End Date | Status | Responsible Team | Milestones & Deliverables
Phase 1: Initial Planning (Q1)
Project Initiation | Define project scope, objectives, and success criteria | 01/01/2025 | 15/01/2025 | In Progress | Strategy Team | Project Charter Approved, Stakeholder Sign-Off
Stakeholder Analysis | Identify key stakeholders and their influence/interest levels | 16/01/2025 | 31/01/2025 | Pending | Project Manager | Stakeholder Matrix Documented
Phase 2: Strategy Development (Q2)
Market Research & Analysis | Conduct SWOT, PESTEL, and competitive landscape analysis | 01/02/2025 | 15/03/2025 | Pending | Research & Insights Team | Comprehensive Market Report Delivered
Strategy Formulation | Create strategic goals, initiatives, and KPIs | 16/03/2025 | 31/03/2025 | Pending | Executive Strategy Committee | Strategic Plan Draft Finalized
Phase 3: Implementation Planning (Q3)
Resource Allocation | Assign personnel, budget, and tools for execution | 01/04/2025 | 15/04/2025 | Pending | Finance & HR Teams | Budget Approved, Team Assignments Confirmed
Timeline & Task Breakdown | Create detailed project roadmap and Gantt chart | 16/04/2025 | 30/04/2025 | Pending | Project Management Office (PMO) | Roadmap and Gantt Chart Published
Phase 4: Execution & Monitoring (Q4)
Implementation Launch | Begin execution of strategic initiatives | 01/05/2025 | 31/12/2025 | Pending | All Departments Involved
Performance Tracking & Review | Monthly review of KPIs, adjust as needed | 01/06/2025 | 31/12/2025 | Pending | PMO & Leadership Team
Template Version: 1.0 ¦ Last Updated: 05/04/2025