## Worksheet
Task | Start Date | End Date | Status | Owner | Dependencies
Project Initiation | 2024-01-05 | 2024-01-10 | In Progress | Jane Smith | N/A
Requirement Gathering | 2024-01-11 | 2024-01-25 | To Do | Mike Johnson | Project Initiation
Strategy Development | 2024-01-26 | 2024-02-15 | To Do | Sarah Lee | Requirement Gathering
Resource Allocation | 2024-02-16 | 2024-03-01 | To Do | David Brown | Strategy Development
Design Phase | 2024-03-02 | 2024-03-31 | To Do | Lisa Wong | Resource Allocation
Development Phase | 2024-04-01 | 2024-05-31 | To Do | Carlos Mendez | Design Phase
Testing & QA | 2024-06-01 | 2024-06-30 | To Do | Amy Patel | Development Phase
Deployment Preparation | 2024-07-01 | 2024-07-15 | To Do | Ruth Kim | Testing & QA
Final Deployment & Go-Live | 2024-07-16 | 2024-07-31 | To Do | Tony Garcia | Deployment Preparation
Post-Launch Review | 2024-08-01 | 2024-08-15 | To Do | Jane Smith | Final Deployment & Go-Live