## Worksheet
Weekly Project Timeline - Strategy Planning
Week # | Start Date | End Date | Key Objective | Status (Progress) | Milestones & Deliverables | Responsible Team/Person | Notes/Comments
Week 1 | 2023-10-02 | 2023-10-08 | Define strategic goals and scope |  | Strategic vision document, goal alignment workshop | Strategy Team Lead | Finalized with leadership approval
Week 2 | 2023-10-09 | 2023-10-15 | Market analysis and competitor benchmarking |  | Competitor report, SWOT analysis, market trends summary | Market Research Team | Data collected from 12 key competitors
Week 3 | 2023-10-16 | 2023-10-22 | Develop high-level strategy framework |  | Strategy roadmap, key initiatives, resource planning | Strategy & Planning Team | Initial version reviewed and shared with stakeholders
Week 4 | 2023-10-23 | 2023-10-29 | Stakeholder alignment and feedback session |  | Feedback summary, revision plan, approval request | Project Manager | Meeting with 8 department heads held on 10/25
Total Progress: