## Project Tracker - Analysis View
Project ID | Project Name | Owner | Status | Start Date | Expected End Date | Actual End Date | % Complete
P001 | Innovation Lab Launch | Sarah Johnson | In Progress | 2024-01-15 | 2024-06-30 | - | 68%
P002 | Cybersecurity Upgrade | Michael Chen | Pending Approval | 2024-02-10 | 2024-11-30 | - | 5%
P003 | Customer Portal Redesign | Linda Rodriguez | Completed | 2023-11-20 | 2024-03-15 | 2024-03-15 | 100%
P004 | Supply Chain Optimization | David Kim | Delayed (2 weeks) | 2023-12-05 | 2024-10-31 | - | 47%
Total Projects: |  |  | 4 |  |  |  | 60%