## Worksheet
Daily Project Tracker - Strategy Planning
Date | Project Name | Objective/Goal | Key Tasks & Milestones | Status (Daily) | Progress (%) | Owner(s) | Risk/Issues
2023-11-05 | Market Expansion Strategy | Enter 3 new markets by Q2 2024 | - Conduct market research - Develop localized marketing plans - Establish partner network | In Progress | 55% | Marketing Team, Alex Johnson | Limited local expertise in Market C
2023-11-05 | New Product Launch - Phase 1 | Complete product design and prototyping by Dec 2023 | - Finalize design specs - Build first prototype - Internal testing plan | On Track | 70% | R&D Team, Sarah Chen | Component delays from supplier X
2023-11-05 | Digital Transformation Initiative | Implement new CRM system by Q1 2024 | - Vendor selection - Data migration planning - User training development | Delayed | 35% | IT Department, James Wilson | Budget approval pending from Finance
2023-11-05 | Client Retention Program | Increase retention rate by 15% in 6 months | - Analyze churn reasons - Develop loyalty incentives - Customer feedback survey rollout | In Progress | 42% | Customer Success, Lisa Thompson | Survey response rate below target
Last Updated:November 5, 2023 ¦Status Legend:On Track,In Progress,Delayed