## Worksheet
Project Tracker - Strategy Planning (Data Version)
Project ID | Project Name | Department | Status | Priority | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date | Budget (USD) | Progress (%)
PJ001 | Market Expansion Initiative | Marketing & Sales | In Progress | High | 2023-10-15 | 2024-03-31 | 2023-10-18 | - | $75,000 | 65%
PJ002 | Product Innovation Lab | R&D | Completed | Medium | 2023-08-01 | 2024-01-31 | 2023-08-05 | 2024-01-15 | $98,500 | 100%
PJ003 | Digital Transformation Phase 1 | IT & Operations | In Progress | High | 2023-09-10 | 2024-06-30 | 2023-11-15 | - | $154,750 | 48%
PJ004 | Employee Development Program | HR & Training | Pending | Medium | 2024-02-01 | 2024-11-30 | - | - | $35,800 | 5%
PJ005 | Customer Experience Overhaul | Customer Success | In Progress | High | 2023-11-01 | 2024-08-31 | 2023-11-05 | - | $67,450 | 73%
Data Version - Last Updated: October 5, 2023 ¦ Generated from Strategy Planning System