## Worksheet
Monthly Project Tracker - Strategy Planning
Project ID | Project Name | Objective | Status | Owner | Scheduled Start Date | Scheduled End Date | Progress (%) | Actions/Notes
PJ001 | Market Expansion Initiative | Enter new regional markets by Q3 | In Progress | Jane Smith | 2024-04-01 | 2024-09-30 | 65% | Finalizing legal compliance; awaiting market analysis report.
PJ002 | Digital Transformation Roadmap | Modernize internal systems by end of year | Planning Phase | Mark Johnson | 2024-04-15 | 2024-12-31 | 15% | Draft architecture approved; stakeholder alignment ongoing.
PJ003 | Customer Retention Program | Increase customer retention by 20% | On Hold | Sarah Lee | 2024-05-10 | 2024-11-30 | 8% | Pending budget approval from finance team.
PJ004 | Innovation Lab Launch | Establish innovation center for R&D projects | Planning Phase | David Kim | 2024-06-01 | 2024-12-15 | 10% | Landing site selection in progress.
Total Projects: | [6 empty] | 28%