## Worksheet
Weekly Project Tracker - Strategy Planning
Project ID | Project Name | Owner | Status | Weekly Progress (Week of [Date]) |  |  | Next Steps | Risk Level
|  |  |  | Mon | Tue | Wed | Thurs
PJ-001 | Market Expansion Strategy | Jane Doe | On Track | Completed: Research Phase A Next: Draft Proposal 1.0 | In Progress: Data Analysis Next: Validate Trends | Closed: Review Meeting Held Next: Finalize Roadmap | Pending Feedback from Stakeholders | Low
PJ-002 | New Product Launch Planning | John Smith | Delayed (1 Week) | In Progress: Market Validation Next: Adjust Timeline | Closed: UX Testing Complete Next: Refine Prototype | Pending Review from Marketing Team | Finalize Branding Guidelines | Medium
PJ-003 | Internal Process Automation | Alice Johnson | Risk Detected: Vendor Delay Next: Alternative Sourcing Plan | Closed: Design Phase Complete Next: Developer Onboarding | In Progress: Integration Testing Next: Finalize API Contracts | Pending Dev Resource Allocation | High
Totals: |  |  | 3 Projects | 1 On Track | 1 Delayed | 1 At Risk
Notes: Weekly updates due every Monday by 9 AM. Status changes must be documented with reason and corrective action.