## Worksheet
Advanced Strategy Planning Schedule Planner
Quarterly Execution Timeline ¦ Q3 2024
Task ID | Project Phase | Description | Owner | Start Date | End Date | Status | % Complete
S-001 | Market Research & Analysis | Conduct competitive landscape and customer segmentation study | Alice Thompson | 2024-07-15 | 2024-08-15 | Completed
S-002 | Strategic Objective Setting | Define KPIs and SMART goals for Q3 initiatives | James Reed | 2024-07-18 | 2024-08-10 | Completed
S-003 | Product Roadmap Development | Create phased feature rollout plan for product suite | Samuel Kim | 2024-08-12 | 2024-09-15 | In Progress
S-004 | Resource Allocation & Budgeting | Finalize team assignments and budget distribution | Lisa Chen | 2024-08-15 | 2024-09-30 | In Progress
S-005 | Stakeholder Alignment Workshop | Host executive review session for strategy approval | Robert Garcia | 2024-09-18 | 2024-09-18 | Delayed (Pending)
S-006 | Execution Launch Phase | Begin first sprint of operational rollout | Elena Martinez | 2024-10-01 | Planned (TBD) | Not Started
Total Tasks |  |  |  |  | 6 | 3 Completed, 2 In Progress, 1 Delayed | 68%