## Worksheet
Strategy Planning Schedule Planner - Client View
Phase | Activity | Start Date | End Date | Status | Responsible Party
Initiation | Define Strategic Objectives | 2023-10-01 | 2023-10-15 | Pending | Client Team
Planning | Market Analysis & SWOT Review | 2023-10-16 | 2023-11-05 | In Progress | Strategy Consultants
Execution Planning | Develop Action Plan & KPIs | 2023-11-06 | 2023-11-20 | Pending | Project Manager
Execution Phase 1 | Launch Pilot Program | 2023-11-21 | 2024-01-31 | Pending | Operations Team
Execution Phase 2 | Scale & Optimize Strategy | 2024-02-01 | 2024-05-31 | Pending | Leadership Team
Evaluation | Performance Review & Reporting | 2024-06-01 | 2024-06-30 | Pending | Analytics Team
Last Updated: October 5, 2023 ¦ Version: Client View - Strategy Planner v1.0