## Worksheet
Strategy Planning - Schedule Planner (Dashboard View)
Task ID | Task Name | Owner | Start Date | Due Date | Progress (%) | Status
SP-001 | Market Research & Analysis | Jane Doe | 2024-04-15 | 2024-05-15 | 85% | On Track
SP-002 | Competitor Benchmarking | John Smith | 2024-04-18 | 2024-05-18 | 63% | Delayed
SP-003 | SWOT Analysis Finalization | Alice Brown | 2024-04-20 | 2024-05-19 | 100% | Completed
SP-004 | Strategic Objective Definition | Mike Wilson | 2024-04-16 | 2024-05-17 | 93% | On Track
SP-005 | Budget Allocation Plan | Sarah Lee | 2024-04-22 | 2024-06-15 | 37% | Delayed
SP-006 | Risk Assessment & Mitigation | David Kim | 2024-04-19 | 2024-05-19 | 58% | On Track
SP-007 | Stakeholder Alignment Workshop | Lisa Chen | 2024-05-10 | 2024-05-11 | 95% | On Track
SP-008 | Final Strategy Document Drafting | Tony Reed | 2024-05-15 | 2024-06-30 | 15% | On Track
Dashboard Summary
Total Tasks: | 8
Completed: | 1
On Track: | 5
Delayed: | 2
Average Progress: | 64%