## Worksheet
STRATEGY PLANNING SCHEDULE PLANNER - DETAILED VERSION
Phase / Milestone | Task Description | Owner | Start Date | End Date | Status | Budget Allocation (USD) | % Complete | Notes / Dependencies
PHASE 1: STRATEGIC ASSESSMENT & RESEARCH
1.1 | Conduct SWOT Analysis (Internal & External) | John Smith | 2023-10-05 | 2023-10-15 | In Progress | $8,500 | 75% | Requires input from Marketing & Finance teams
1.2 | Market Trend Analysis (Last 3 Years) | Lisa Chen | 2023-10-06 | 2023-10-18 | In Progress | $6,200 | 55% | Data from industry reports and databases required
1.3 | Competitor Benchmarking Report | Michael Brown | 2023-10-08 | 2023-10-25 | Completed | $9,750 | 100% | Finalized on 2023-10-24
PHASE 2: STRATEGY FORMULATION & DESIGN
2.1 | Develop Long-Term Vision Statement (5-Year) | Sarah Johnson | 2023-10-16 | 2023-10-30 | In Progress | $5,500 | 45% | Draft approved by leadership on 2023-10-19
2.2 | Create Strategic Objectives Matrix (SMART) | David Wilson | 2023-10-17 | 2023-11-05 | Delayed | $4,800 | 35% | Waiting on executive feedback; scheduled review 11/02
PHASE 3: ACTION PLAN & RESOURCE ALLOCATION
3.1 | Design Departmental Roadmaps (Q4 2023 - Q1 2025) | Amanda Lee | 2023-11-06 | 2023-11-30 | Completed | $15,400 | 100% | Submitted on 2023-11-28; approved by all leads
PHASE 4: EXECUTIVE REVIEW & FINAL APPROVAL
4.1 | Present Strategy to Board of Directors | Robert Taylor | 2023-12-05 | 2023-12-07 | Completed | $8,950 | 100% | Presentation delivered on 2023-12-06; approval granted
TOTAL PROJECT SUMMARY |  |  |  |  | $69,100