## Worksheet
Strategy Planning - Extended Schedule Planner
Task ID | Task Name | Owner | Planned Dates |  |  |  | Duration (Days) | Priority | Status
|  |  | Start Date | End Date | Due Date | Milestone Target
Phase 1: Research & Analysis
SR-001 | Market Landscape Review | Marketing Team | 2024-04-01 | 2024-04-15 | 2024-04-15 | N/A | 15 | High | In Progress
SR-002 | Customer Needs Assessment | Product Research Team | 2024-04-16 | 2024-05-15 | 2024-05-15 | N/A | 30 | High | In Progress
Milestone: Research Completion |  |  |  | 2024-05-15 | Finalize All Research Reports |  |  | Completed - 2024-05-16
Phase 2: Strategy Development
SD-001 | Core Vision & Objectives Definition | C-Level Team | 2024-05-16 | 2024-05-31 | 2024-05-31 | N/A | 16 | High | In Progress
SD-002 | Digital Transformation Roadmap Draft | IT Strategy Team | 2024-06-01 | 2024-06-30 | 2024-06-30 | N/A | 31 | Medium | In Progress
Milestone: Strategy Draft Review |  |  |  | 2024-06-30 | Review and Approve Draft Strategy Document |  |  | Pending Review - 2024-07-15
Phase 3: Execution Planning
EP-001 | Resource Allocation & Budgeting | Finance Department | 2024-07-01 | 2024-07-31 | 2024-07-31 | N/A | 31 | High | In Progress
EP-002 | Tactical Implementation Plan Finalization | Project Management Office | 2024-08-01 | 2024-08-31 | 2024-08-31 | N/A | 31 | High | Delayed - Due 2024-09-15
Milestone: Final Strategy Approval |  |  |  | 2024-09-15 | CEO & Board Approval of Full Plan |  |  | Pending - Next Review: 2024-09-16
Overall Status Summary - 85% Complete
This document is a strategic schedule planner for the Extended Strategy Planning Cycle. Last updated on April 5, 2024.