## Worksheet
Large Business Strategy Planning Schedule
Phase/Activity | Key Milestones |  |  |  | Timeline (Q) |  |  | Responsible Team | Status
| Objective | Deliverable | Owner (Role) | Approval Required? | Q1 2024 | Q2 2024 | Q3 2024
Executive Strategy Initiation | Define long-term vision and objectives | Strategy Charter Document v1.0 | CPO, CFO, CEO | Yes | ✓ |  |  | Executive Board | Ongoing
Market & Competitive Analysis | Assess external environment and market trends | Industry Benchmark Report v1.0 | Strategy Research Team | No | ✓ |  |  | Market Intelligence | Ongoing
Internal Capability Assessment | Evaluate current resources, skills, and processes | Internal Audit & Readiness Scorecard | HR & Operations Lead | No | In Progress (Q1) |  |  | Corporate Strategy Office | Ongoing
Business Unit Alignment Workshop | Secure cross-functional buy-in and alignment | Alignment Agreement (Signed) | COO, Department Heads | Yes | Target: Q2 2024 |  |  | Leadership Team | Delayed
Strategic Roadmap Development | Develop detailed 3-year strategic plan with KPIs | 2024–2026 Strategic Plan v1.0 | Strategy Lead, Finance | Yes | Target: Q3 2024 (Draft) |  |  | Strategy & Planning Division | Ongoing
Resource Allocation Review | Align budget, people, and technology with strategy | Capital & Resource Plan v1.0 | CFO, CTO, HR Director | Yes | Target: Q3 2024 (Final) |  |  | Finance & Operations | Ongoing
Board Presentation & Approval | Present finalized strategy to Board of Directors | Approved Strategic Plan Document | CFO, CEO, Strategy Lead | Yes | Target: Q4 2024 (Final) |  |  | Executive Leadership Team | Ongoing
Execution Kick-Off & Monitoring Framework | Launch implementation with governance model | Execution Dashboard & Governance Calendar | Project Management Office (PMO) | Target: Q4 2024 (Start) |  |  | PMO & Strategy Team | Ongoing
Total Phases Completed | [7 empty] | 5 / 8