## Worksheet
Strategy Planning - Schedule Planner
Week / Date | Action Item | Responsible Team | Status | Deadline | Notes / Updates
Week 1 Jan 01 - Jan 07 | Define strategic objectives | Executive Team | Pending | Jan 05
Week 2 Jan 08 - Jan 14 | Market research & competitor analysis | Marketing Team | In Progress | Jan 12 | Data collection ongoing; initial insights by Jan 10.
Week 3 Jan 15 - Jan 21 | SWOT Analysis Workshop | All Departments | Pending | Jan 18 | Scheduled for Thursday at 2 PM.
Week 4 Jan 22 - Jan 28 | Develop action plan & KPIs | Strategy Team | Pending | Jan 25
Week 5 Jan 29 - Feb 04 | Review and finalize strategy document | Leadership Board | Pending | Feb 03
Week 6 Feb 05 - Feb 11 | Communicate strategy to all teams | HR & Communications | Pending | Feb 08 | Training session scheduled for Feb 9.
Week 7 Feb 12 - Feb 18 | Begin implementation of Phase 1 | All Operational Teams | Pending | Feb 15
Week 8 Feb 19 - Feb 25 | Mid-point review & adjust strategy as needed | Strategy Team | Pending | Feb 23
Key Milestones & Deliverables Summary
Strategic Plan Finalized |  | February 3, 2024
Phase 1 Implementation Starts |  | February 15, 2024
Mid-Strategy Review Complete |  | February 23, 2024