## Worksheet
Strategy Planning - Schedule Planner (Report Version)
Quarterly Execution Timeline ¦ Q2 2024
Task ID | Project Phase | Key Activities |  |  | Timeline & Milestones |  |  | Responsible Team | Status
|  | Activity Description | Owner (Role) | Dependencies | Start Date | Target Completion | Status Tracking
P001 | Initiation | Define strategic objectives and scope alignment | Project Manager | Executive Approval, Market Research Report | 2024-04-01 | 2024-04-15 | Pending Review | Sales & Strategy Group | In Progress
P002 | Planning | Develop detailed roadmap and resource allocation plan | Planning Lead | Strategic Objectives, Budget Approval | 2024-04-16 | 2024-05-10 | In Progress - 75% | Operations Team | In Progress
P003 | Execution | Deploy new market entry initiatives (Phase 1) | Product Director | Final Roadmap Sign-Off, Team Onboarding | 2024-05-13 | 2024-06-30 | Pending Launch Readiness Review | R&D & Marketing Teams | Delayed (Pending)
P004 | Monitoring | Establish KPI dashboards and real-time tracking system | Data Analyst | Execution Phase 1, System Integration Team Output | 2024-06-01 | 2024-06-30 | In Progress - 55% | Data & Analytics Unit | In Progress
P005 | Review & Optimize | Conduct Q2 retrospective and adjust strategy for next quarter | Strategy Director | All active projects, Performance Reports from KPIs | 2024-07-01 | 2024-07-15 | Not Started | Executive Strategy Council | Planned
Total Projects |  |  |  | 5 |  |  | 3 In Progress ¦ 1 Delayed ¦ 1 Planned | —
Report generated on: June 4, 2024 ¦ Prepared by Strategy Planning Office ¦ Confidential