## Worksheet
Small Business Strategy Planning Schedule
Task / Activity | Responsible Team | Start Date | End Date | Status
Define Business Vision & Mission | Leadership Team | 2024-01-05 | 2024-01-15 | Completed
Market Research & Competitor Analysis | Marketing Team | 2024-01-16 | 2024-01-31 | Completed
SWOT Analysis Review | Strategy Committee | 2024-02-01 | 2024-02-15 | Completed
Milestone: Finalize Strategic Goals (Q1) | Leadership Team | 2024-02-16 | 2024-03-15 | Completed
Create 90-Day Action Plan | Operations Team | 2024-03-16 | 2024-04-30 | Completed
Resource Allocation & Budgeting | Finance Team | 2024-05-01 | 2024-05-15 | In Progress
Team Training & Onboarding Plan | Hr Department | 2024-05-16 | 2024-06-30 | In Progress
Milestone: Launch New Product Line (Q2) | Product Development Team | 2024-06-01 | 2024-07-31 | Delayed
Customer Feedback & Iteration Cycle | Customer Success Team | 2024-08-01 | 2024-10-31 | To Do
Review & Adjust Strategy (Mid-Year) | Executive Committee | 2024-09-15 | 2024-10-31 | To Do
Milestone: Q3 Performance Review & Planning (Q3) | Leadership Team | 2024-10-01 | 2024-11-30 | To Do