## Team Strategy Planning Schedule
Week | Task / Activity | Owner | Start Date | End Date | Status
Week 1 | Define strategic objectives and KPIs | John Doe | 2024-04-01 | 2024-04-05 | In Progress
| Conduct team alignment workshop | Jane Smith | 2024-04-03 | 2024-04-05 | Pending
| Review market analysis report | Mike Johnson | 2024-04-01 | 2024-04-06 | In Progress
Week 2 | Develop quarterly action plan | Emily Chen | 2024-04-08 | 2024-04-12 | Pending
| Assign project roles and responsibilities | David Brown | 2024-04-10 | 2024-04-11 | Pending
| Set up collaboration tools (Slack, Trello) | Sarah Wilson | 2024-04-08 | 2024-04-13 | In Progress
Week 3 | Present strategy draft to leadership | John Doe | 2024-04-15 | 2024-04-16 | Pending
| Collect feedback and revise plan | Jane Smith | 2024-04-17 | 2024-04-19 | Pending
| Finalize strategy document and approvals | Emily Chen | 2024-04-20 | 2024-04-21 | Pending
Week 4 | Kick-off meeting: Strategy Execution | David Brown | 2024-04-23 | 2024-04-23 | Pending
| Begin quarterly deliverables tracking | Sarah Wilson | 2024-04-24 | 2024-05-31 | Pending
| Monitor progress with weekly check-ins | All Team Members | 2024-04-25 | Ongoing | Pending
Notes:This schedule is for team use in strategic planning. Status updates should be revised bi-weekly.