## Worksheet
Strategy Planning - Schedule Planner (Tracking View)
Task ID | Task Name | Description | Start Date | End Date | Status | Owner | % Complete
T001 | Market Research Phase 1 | Analyze current market trends and customer needs. | 2024-04-01 | 2024-04-15 | Completed | Alice Johnson | 100%
T002 | Competitor Analysis | Identify key competitors and their strategies. | 2024-04-16 | 2024-04-30 | In Progress | Bob Smith | 75%
T003 | SWOT Analysis | Evaluate internal strengths, weaknesses and external opportunities. | 2024-05-01 | 2024-05-15 | In Progress | Carol White | 60%
T004 | Strategic Goal Setting | Define long-term goals and KPIs. | 2024-05-16 | 2024-05-31 | Delayed | David Lee | 35%
T005 | Resource Allocation Plan | Assign personnel and budget to strategic initiatives. | 2024-06-01 | 2024-06-15 | In Progress | Eva Brown | 50%
T006 | Execution Timeline Development | Create detailed project timeline with milestones. | 2024-06-16 | 2024-07-15 | Delayed | Frank Wilson | 25%
T007 | Stakeholder Review Meeting | Presentation and feedback session with leadership team. | 2024-07-16 | 2024-07-31 | In Progress | Gina Martinez | 45%
Total Tasks:7 ¦Completed:1 ¦In Progress:4 ¦Delayed:2