## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Budget Allocated ($) | Actual Spend ($) | Variance ($)
T-001 | Market Analysis Phase | Marketing Team | 2024-03-01 | 2024-03-15 | High | In Progress | 15,000.00 | 9,250.75 | +5,749.25
T-002 | Product Development Sprint | R&D Department | 2024-03-05 | 2024-03-31 | Medium | In Progress | 55,000.00 | 32,150.30 | +22,849.70
T-003 | Customer Feedback Integration | Product Team | 2024-03-10 | 2024-03-25 | High | Pending | 12,500.00 | 2,375.00 | +10,125.00
T-004 | Launch Campaign Planning | Marketing Team | 2024-03-15 | 2024-04-15 | Medium | Not Started | 35,000.00 | 1,256.45 | +33,743.55
T-005 | Financial Forecast Modeling | Finance Department | 2024-03-20 | 2024-04-10 | Low | Not Started | 22,500.00 | 752.34 | +21,747.66
Total | [6 empty] | 140,000.00 | 45,784.84 | +94,215.16