## Worksheet
Task ID | Task Name | Assigned To | Department | Start Date | End Date | Priority | Status | Progress (%)
T001 | Develop Market Entry Strategy | Sarah Johnson | Marketing | 2024-01-15 | 2024-03-31 | High | In Progress | 65
T002 | Conduct Competitor Analysis | Michael Brown | Strategy | 2024-01-10 | 2024-02-28 | Medium | Completed | 100
T003 | Draft Quarterly Roadmap | Emily Davis | Product Management | 2024-01-20 | 2024-03-15 | High | In Progress | 40
T004 | Finalize Budget Allocation | James Wilson | Finance | 2024-01-18 | 2024-03-10 | Medium | In Progress | 70
T005 | Launch Pilot Program | Lisa Martinez | Operations | 2024-03-01 | 2024-05-31 | High | Not Started | 0
T006 | Update Risk Assessment Report | Robert Taylor | Risk Management | 2024-01-25 | 2024-03-31 | Low | Not Started | 0