## Worksheet
Task ID | Task Description | Owner | Due Date | Status | Prioritization Level
T001 | Define long-term vision and mission statements | CEO & Strategy Team | 2023-12-31 | In Progress | High
T002 | Conduct SWOT analysis for current market position | Market Research Team | 2023-11-30 | To Do | High
T003 | Identify key performance indicators (KPIs) for Q1 2024 | Operations & Analytics Team | 2023-11-25 | Completed | Medium
T004 | Develop quarterly strategic goals and OKRs | Leadership Team | 2023-12-15 | In Progress | High
T005 | Review competitive landscape and benchmarking data | Competitive Intelligence Unit | 2023-11-28 | To Do | Medium
T006 | Align departmental plans with corporate strategy | Department Heads & PMO | 2023-12-10 | In Progress | High
T007 | Present strategy draft to executive board for feedback | Strategy Manager | 2023-12-20 | To Do | High
T008 | Finalize strategic roadmap and publish for organization-wide review | Strategic Planning Office | 2024-01-15 | To Do | Medium
T009 | Establish cross-functional working groups for implementation planning | HR & PMO | 2023-12-31 | To Do | Medium
T010 | Prepare training and communication plan for new strategy rollout | Communications & L&D Teams | 2024-01-31 | To Do | Low