## Worksheet
Weekly Planner - Strategy Planning
Analysis View
Task / Objective | Week of: [Insert Date]
| Mon | Tue | Wed | Thu | Fri | Sat | Sun
Strategic Goals & Initiatives
Refine Q3 Market Expansion Strategy Priority: High | • Review competitive landscape • Draft regional focus areas | • Finalize market selection matrix • Schedule team alignment meeting | • Begin financial modeling for top 3 regions | • Present draft strategy to leadership | Review feedback & iterate
Launch New Product Feature MVP Priority: High | • Finalize wireframes • Assign development sprint tasks | • Kick off development phase • Set up testing framework | • Conduct internal usability check | • Begin beta user recruitment | Monitor early feedback Collect usage data
Evaluate Customer Retention Metrics Priority: Medium | • Pull churn rate data • Analyze drop-off points | • Identify top 3 retention risk areas | • Propose 2 improvement initiatives | Present findings to product team | Begin A/B testing for one initiative
Key Performance Indicators (KPIs)
Customer Acquisition Cost (CAC) | Target: $85 Actual: $87.20 | Target: $84 Actual: $86.10 | Target: $83 Actual: $92.50 | Trend: ↑ 5% | Target: $82 Actual: $91.30
Monthly Recurring Revenue (MRR) | $145,000 | $152,300 | $158,900 | $162,450 | ↑ +3.4%
Net Promoter Score (NPS) | 48 | 50 | 46 | ↓ -2 pts | 51
Risk Assessment & Dependencies
Supply Chain Delays (Vendor X) Impact: High ¦ Likelihood: Medium | • Monitor delivery timelines • Prepare contingency plan by Thursday • Escalate to procurement if delay exceeds 5 days
Regulatory Update on Data Compliance Impact: Critical ¦ Likelihood: Low | • Track official announcements • Schedule legal review session by Friday • Prepare compliance checklist for team training
Total Activities Completed: | 14/18 | 15/18 | 9/13 | 6/9 | 5/7
Generated on [Insert Date] ¦ Version 1.0 ¦ Status: In Progress This is an Analysis View for Strategy Planning – Weekly Planner Template