## Worksheet
Study Organizer - Business Plan (Manager View)
Comprehensive Project Overview & Performance Tracking
Project Phase | Key Objective | Deadline | Status | Responsible Team Member | Budget Allocated ($)
Market Research | Identify target student demographics and learning preferences | 2025-04-15 | In Progress | Jane Doe (Research Lead) | 3,500.00
Curriculum Development | Create structured study modules aligned with academic goals | 2025-04-30 | Not Started | Mark Wilson (Content Director) | 12,800.00
Technology Integration | Deploy platform with interactive learning tools and analytics dashboard | 2025-05-15 | In Progress | Lisa Chen (Tech Lead) | 8,200.00
Pilot Testing | Run controlled test with 15 students to evaluate effectiveness | 2025-06-15 | Not Started | Robert Kim (QA Manager) | 4,000.00
Marketing & Outreach | Promote study program via campus events and digital channels | 2025-06-30 | Not Started | Sarah Johnson (Marketing Director) | 7,500.00
Full Rollout Preparation | Finalize documentation and train support staff for launch | 2025-07-15 | Not Started | Alex Rivera (Operations Lead) | 3,900.00
Project Summary
Total Budget:$40,900.00
Completed Tasks:1 / 6 (16.7%)
Status Indicator:On Track – 2 tasks in progress, rest scheduled.
© 2025 Study Organizer - Business Plan (Manager View) ¦ Generated on October 17, 2023